## Worksheet4_Q1
Table 1 : Activity duration |  |  | Table 2 : Activity Progress
Task | Estimated Duration (days) | Actual Finish | Time (actual day) | Planned Progress | Actual Progress
1. Orbital Mechanics | 20 | 31 | 0 | 0 | 0
2.1. Time Tracking | 2 | 1 | 5 | 11.5823 | 20
2.2. Camera Angle | 3 | 4 | 10 | 23.1646 | 23
2.3. Camera Fly-Through | 8 | 4 | 15 | 34.7468 | 28
2.4. Bookmarks | 2 | 2 | 20 | 46.3291 | 28
3.1. Orbit Visualisation | 5 | 3 | 25 | 57.9114 | 41
3.2. Textures | 5 | 11 | 30 | 69.4937 | 41
3.3. Popup Labels | 3 | 9 | 35 | 81.0759 | 61
4.1. Planet Rendering | 13 | 24 | 40 | 92.6582 | 69
4.2. Star Rendering | 8 | 35 | 45 | 104.2405
4.3. Asteroid Rendering | 20 |  | 50 | 115.8228
4.4. Spacecraft Rendering | 20 |  | 55 | 127.4051
5.1. Solar System Data Entry | 13 |  | 60 | 138.9873
5.2. Star/Galaxy Data Entry | 40 |  | 65 | 150.5696
5.3. Extrasolar Planet Data Entry | 13 |  | 70 | 162.1519
5.4. Spacecraft Data Entry | 8 |  | 75 | 173.7342
|  |  | 80 | 185.3165
Sum of Task Durations | 183 |  | 85
Planned Project Duration | 79 |  | 90
Planned Progress per Day | 2.3165 |  | 95
100
Note on B21: Where did we get this from? In principle, this comes from our AOA or AON graph, but just take it as given in this scenario.